## Before_vs_After
Category | Before (Java + TestNG) | After (Playwright + TypeScript)
Language | Java | TypeScript
Framework | TestNG + Selenium | Playwright Test
Execution Speed | Slow | 30–50% Faster
Parallel Execution | Limited | Built-in Parallelism
Browser Support | Mostly Chrome | Chromium / Firefox / WebKit
Flakiness | High | Low (Auto-waiting)
API Testing | RestAssured | Playwright API Context
GraphQL | Separate Library | Native HTTP
Data Driven | TestNG DataProvider | JSON / CSV / Fixtures
Reporting | Surefire / Custom | HTML / Allure / JSON
Observability | Limited Logs | Traces / Screenshots / Network
Maintenance Cost | High | Lower

## Estimation
Phase | Activity | Effort (Person-Days)
Assessment | Framework & Test Inventory | 5
Framework Setup | Playwright Framework Setup | 7
Migration | 1000 Test Case Conversion | 250
Workflow | 125 Workflow Refactoring | 25
API & GraphQL | REST + GraphQL Migration | 25
Test Data | 50MB Test Data Conversion | 6
Reporting | Jira, Grafana, PowerBI Integration | 10
CI/CD | Pipeline Setup | 4
Stabilization | Debugging & Optimization | 10
Buffer | Risk & Contingency | 15

## Summary
Metric | Value
Total Test Cases | 1000
Total Workflows | 125
Test Data Size | 50 MB
QA Resources | 2
Total Effort (Person-Days) | 360
Estimated Duration (Weeks) | 18
Estimated Cost (@ ₹8k/day) | ₹28.8 Lakhs