## Summary
Metric | Value
Total Test Cases | 1000
Total Workflows | 125
Test Data Size | 50 MB
QA Resources | 2
Total Effort (Person-Days) | 360
Estimated Duration (Weeks) | 18
Estimated Cost (@ ₹8k/day) | ₹28.8 Lakhs
This migration is a strategic investment that reduces execution time, lowers maintenance cost, improves quality visibility, and future-proofs our automation strategy.
Risk & Mitigation (Leadership Confidence)
Risk | Mitigation |  |  | Risk | Mitigation
Initial migration cost | One-time investment, long-term savings |  |  | Skill gap in TS | Enable TypeScript linting & templates
Skill transition (Java → TS) | Structured templates & code standards |  |  | Selector instability | Use getByRole, getByTestId
Parallel frameworks | Phased migration (no big-bang) |  |  | Reporting mismatch | Dual-run Java & Playwright initially
Reporting mismatch | Dual-run until parity achieved |  |  | Data dependency | API-driven test data setup
this is a technical-manager / leadership-ready answer. I’ll break it into three crisp sections so you can directly reuse it in estimation decks, Excel, or architecture reviews.
1️⃣ Detailed Effort & Cost Estimation Sheet |  |  |  | Reporting & Observability Migration
Automation Migration: Java → Playwright (TypeScript) |  |  |  | Reporting Flow (Target)
📌 Input Assumptions |  |  |  | Tool | How
|  |  |  | Playwright HTML | Default execution reports
Parameter | Value |  |  | Allure | Rich test analytics
Total test cases | 1000 |  |  | Jira | REST API to push execution results
Test scenarios | 150 |  |  | Grafana | Metrics from CI + JSON reports
Workflows | 125 |  |  | PowerBI | Consume Playwright JSON / JUnit
Test data size | 50 MB |  |  | Splunk | CI logs + Playwright traces
Existing framework | Java + TestNG + Hybrid (POM + Data-Driven)
Target framework | Playwright + TypeScript |  |  | Key Metrics Preserved
QA resources | 2 Automation QAs
Complexity | Medium–High (UI + API + GraphQL + Reporting) |  |  | Pass / Fail trends
Execution duration
🧮 Effort Estimation Breakdown (Excel-Ready)
Flakiness rate
Sheet 1: Activity-wise Effort
Module-wise coverage
Phase | Activity | Scope | Effort (Person-Days)
Assessment | Framework & test inventory | 1,000 TC | 3 | Environment stability
| Dependency & data analysis | 50MB | 2
Framework Setup | Playwright infra & config | Base setup | 3
| POM + fixture design | Reusable components | 4
Conversion | Java → TS test conversion | 1,000 TC @ 4 TC/day | 250
| Workflow refactoring | 125 flows | 25
API & GraphQL | REST migration | ~300 TC | 15
| GraphQL migration | ~100 TC | 10
Data | Test data restructuring | JSON/CSV | 6
Reporting | Jira integration | Execution sync | 3
| Grafana metrics | Dashboards | 3
| PowerBI dataset | Management view | 4
CI/CD | Pipeline setup | Jenkins/GH Actions | 4
Stabilization | Debug & flakiness fix | Regression runs | 10
Buffer | Risk & unknowns (~10%) | — | 15
Total |  |  | 360 Person-Days
Sheet 2: Resource & Timeline
Resource | Allocation | Duration
QA-1 | 100% | 18 weeks
QA-2 | 100% | 18 weeks
Total Duration |  | ~18 weeks (4.5 months)
Sheet 3: Cost Estimation (Example)
(Replace rate as per org)
Item | Value
Avg cost / QA / day | ₹8,000
Total person-days | 360
Total Cost | ₹28.8 Lakhs
2️⃣ Java → Playwright Code Conversion Examples
🔁 Test Case Conversion
Java + TestNG
@Test
public void loginTest() {
LoginPage login = new LoginPage(driver);
login.login("user", "pwd");
Assert.assertTrue(dashboard.isLoaded());
}
Playwright + TypeScript
test('login test', async ({ page }) => {
const login = new LoginPage(page);
await login.login('user', 'pwd');
await expect(page.locator('#dashboard')).toBeVisible();
});
🔁 Data-Driven Conversion
Java (DataProvider)
@DataProvider
public Object[][] users() {
return new Object[][] {{"user1","pwd1"},{"user2","pwd2"}};
}
Playwright (JSON)
const users = require('../data/users.json');
for (const user of users) {
test(`login ${user.name}`, async ({ page }) => {
await login.login(user.username, user.password);
});
}
🔁 REST API Migration
RestAssured
given().body(payload)
.when().post("/login")
.then().statusCode(200);
Playwright API
const response = await request.post('/login', { data: payload });
expect(response.status()).toBe(200);
3️⃣ CI/CD + Grafana + PowerBI Reference Architecture
🏗️ Architecture Flow
Developer Commit
↓
CI Pipeline (Jenkins / GitHub Actions)
↓
Playwright Test Execution
(UI + API + GraphQL)
↓
Artifacts Generated
(HTML / JSON / JUnit / Traces)
↓
┌───────────────┬───────────────┬───────────────┐
│ Jira │ Splunk │ Metrics Store │
│ Test Results │ Logs/Traces │ JSON/Prom │
└───────┬───────┴───────┬───────┴───────┬───────┘
↓ ↓ ↓
Grafana PowerBI Alerts
(Ops & QA) (Mgmt Dashboard) (Failures)
📊 Reporting Responsibilities
Tool | Purpose
Jira | Test execution & defect traceability
Grafana | Flakiness, MTTR, execution trends
PowerBI | Release-level QA health
Splunk | Root cause & failure analytics
🎯 KPIs to Track
Automation coverage %
Pass/fail trend
Avg execution time
Flaky test rate
Defect leakage
✅ Executive Summary (1-Slide Ready)
Effort: ~360 person-days
Timeline: ~4.5 months (2 QAs)
Outcome:
30–40% faster execution
Unified UI + API + GraphQL testing
Lower maintenance & flakiness
Strong observability & reporting

## Sheet1
What Changed vs Java Framework
Area | Java + TestNG | Playwright
Execution | Selenium-based | Native browser engines
Speed | Slower | 30–50% faster
UI + API | Separate tools | Unified
Flakiness | High | Low
Observability | Limited | Built-in traces & logs
2️⃣ Migration Justification for Leadership
🎯 Why This Migration Is Necessary (Business View)
Current Java-based automation framework is functional but no longer scalable for:
Growing regression size (1,000+ test cases)
Multi-browser coverage
Faster release cycles
Real-time observability & analytics
Playwright directly addresses these limitations while reducing long-term cost.
3️⃣ Key Leadership Justifications (Slide-Ready)
🔹 1. Faster Time-to-Market
⚡ 30–40% reduction in execution time
Parallel browser execution out of the box
Faster CI feedback → quicker releases
Impact: Release cycles shortened by days, not hours.
🔹 2. Reduced Maintenance Cost
No WebDriver dependency
Auto-waiting & stable selectors
Less flaky test triage
Impact: QA effort shifts from fixing tests → improving coverage.
🔹 3. Unified Testing Strategy
UI + REST + GraphQL in one framework
Shared test data, auth, and environment setup
Impact: Lower tooling overhead and simplified onboarding.
🔹 4. Enterprise-Grade Observability
Native Playwright traces, screenshots, network logs
Seamless integration with Splunk, Grafana, PowerBI
Impact: Faster root-cause analysis and data-driven QA decisions.
🔹 5. Better Management Visibility
PowerBI dashboards for:
Release quality
Automation coverage
Flakiness trends
Jira-linked execution & defect traceability
Impact: Leadership gets predictable quality signals, not surprises.

## Estimation
Phase | Activity | Effort (Person-Days)
Assessment | Framework & Test Inventory | 5
Framework Setup | Playwright Framework Setup | 7
Migration | 1000 Test Case Conversion | 250
Workflow | 125 Workflow Refactoring | 25
API & GraphQL | REST + GraphQL Migration | 25
Test Data | 50MB Test Data Conversion | 6
Reporting | Jira, Grafana, PowerBI Integration | 10
CI/CD | Pipeline Setup | 4
Stabilization | Debugging & Optimization | 10
Buffer | Risk & Contingency | 15

## Before_vs_After
Category | Before (Java + TestNG) | After (Playwright + TypeScript)
Language | Java | TypeScript
Framework | TestNG + Selenium | Playwright Test
Execution Speed | Slow | 30–50% Faster
Parallel Execution | Limited | Built-in Parallelism
Browser Support | Mostly Chrome | Chromium / Firefox / WebKit
Flakiness | High | Low (Auto-waiting)
API Testing | RestAssured | Playwright API Context
GraphQL | Separate Library | Native HTTP
Data Driven | TestNG DataProvider | JSON / CSV / Fixtures
Reporting | Surefire / Custom | HTML / Allure / JSON
Observability | Limited Logs | Traces / Screenshots / Network
Maintenance Cost | High | Lower